## Bug Report of Salonet vendor ap
BUG REPORT TITILE |  |  |  |  | TEST CASE LINK |  |  |  |  | TEST NUMBER |  |  | TEST DATE
Test of salonet vendor app |  |  |  |  | TEST CASE FOR SALONET APP |  |  |  |  | 1 |  |  | 2022-06-25
BUG REPORT DESCRIPTION |  |  |  |  | BUG DETECTED BY |  |  |  |  | TEST EXECUTED BY |  |  | BUG REPORT DATE
Working of salonet vendor app |  |  |  |  | Gaurank |  |  |  |  | Gaurank |  |  | 2022-06-25
STEP NO | BUG ID | DATE | MODULE or SUBMODULE | BUG DESCRIPCTION | STEP TO REPRODUCE | SEVERITY | PRIORITY | BUG TYPE | ASSIGNED TO DEVELOPER | DEVELOPER COMMENTS | ASSIGNED BY | TESTER COMMENTS | ATTACHMENT | BUG STATUS
15 | BG01 | 2022-06-27 | Login | It gives error saying enter password at the place of enter valid email id | Writing Invalid Mobile Number | Minor | low | UI | ----------- | ------------------- | Gaurank | ------------------- |  | OPEN
18 | BG02 | 2022-06-27 |  | It gives error saying email and password not matched at the place of enter valid email id | Writing Invalid Password With Invalid Mobile Number | Minor | low | UI | ----------- | ------------------- | Gaurank | ------------------- |  | OPEN
20 | BG03 | 2022-06-27 |  | It gives error saying enter password at the place of enter valid email id | Login with registered mobile number | Minor | low | UI | ----------- | ------------------- | Gaurank | ------------------- |  | OPEN
21 | BG04 | 2022-06-27 |  | Error not given after so many wrong password entered | Enter wrong current password many times | Minor | low | UI | ----------- | ------------------- | Gaurank | ------------------- |  | OPEN
24 | BG05 | 2022-06-27 |  | wrong error given it displayed id and password not matched | Login With Unregistered But Valid Login Email Id Only | Minor | low | UI | ----------- | ------------------- | Gaurank | ------------------- |  | OPEN
25 | BG06 | 2022-06-27 |  | wrong error given it displayed id and password not matched | Login With Valid Unregister Login Email Id And Unregistered Password Only | Minor | low | UI | ----------- | ------------------- | Gaurank | ------------------- |  | OPEN
26 | BG07 | 2022-06-27 |  | Error not given is says enter password | Login With Unregistered Valid Login Password Only | Minor | low | UI | ----------- | ------------------- | Gaurank | ------------------- |  | OPEN
35 | BG09 | 2022-06-27 | Forgot Password | No error given for enter valid email id | Reset Password With Invalid Email Id | Minor | low | UI | ----------- | ------------------- | Gaurank | ------------------- |  | OPEN
39 | BG10 | 2022-06-27 | Create New account | No hint available | "Enter Valid Character On First Name" Hint | Minor | low | UI | ----------- | ------------------- | Gaurank | ------------------- |  | OPEN
40 | BG11 | 2022-06-27 |  | No error given | Entering Numeric Character And Special Character On First Name | Minor | low | UI | ----------- | ------------------- | Gaurank | ------------------- |  | OPEN
43 | BG12 | 2022-06-27 |  | No hint available | "Enter Valid Character On Last Name" Hint | Minor | low | UI | ----------- | ------------------- | Gaurank | ------------------- |  | OPEN
44 | BG13 | 2022-06-27 |  | No error given | Entering Numeric Character And Special Character On Last Name | Minor | low | UI | ----------- | ------------------- | Gaurank | ------------------- |  | OPEN
62 | BG14 | 2022-06-27 |  | No hint available | Any Character Hint Provide in password while setting password | Minor | low | UI | ----------- | ------------------- | Gaurank | ------------------- |  | OPEN
68 | BG15 | 2022-06-27 |  | No error given | Same Time Section On Start And End Time | Minor | low | UI | ----------- | ------------------- | Gaurank | ------------------- |  | OPEN
69 | BG16 | 2022-06-27 |  | No error given | Entering 23 Hour Time Or More Than Working Hour | Minor | low | UI | ----------- | ------------------- | Gaurank | ------------------- |  | OPEN
70 | BG17 | 2022-06-28 |  | Slot provided but minutes not showing | Entering Minutes With Hours | Minor | low | UI | ----------- | ------------------- | Gaurank | ------------------- |  | OPEN
79 | BG18 | 2022-06-28 | Change Password in profile section with valid and invalid password | Password saved | password saved with Special character only | Minor | low | UI | ----------- | ------------------- | Gaurank | ------------------- |  | OPEN
80 | BG19 | 2022-06-28 |  | Password saved | password saved with Numbers only | Minor | low | UI | ----------- | ------------------- | Gaurank | ------------------- |  | OPEN
81 | BG20 | 2022-06-28 |  | Password saved | password saved with Upper case | Minor | low | UI | ----------- | ------------------- | Gaurank | ------------------- |  | OPEN
82 | BG21 | 2022-06-28 |  | Password saved | password saved with lower case | Minor | low | UI | ----------- | ------------------- | Gaurank | ------------------- |  | OPEN
84 | BG22 | 2022-06-28 |  | Password saved | password saved with Character length only one | Minor | low | UI | ----------- | ------------------- | Gaurank | ------------------- |  | OPEN
85 | BG23 | 2022-06-28 |  | Password saved | password saved with Character length to 60 | Minor | low | UI | ----------- | ------------------- | Gaurank | ------------------- |  | OPEN
87 | BG24 | 2022-06-28 | Change profile | No back or cancel button available | No back or cancel button is available at profile photo change even mobile back button also not working | Minor | low | FC | ----------- | ------------------- | Gaurank | ------------------- |  | OPEN
88 | BG25 | 2022-06-28 |  | Problem while saving profile photo from Google gallery | Sometimes changed but some time not changed and no error given if not change profile image with Google images gallery option problem in android 11 | Minor | low | FC | ----------- | ------------------- | Gaurank | ------------------- |  | OPEN
89 | BG26 | 2022-06-28 |  | Problem while saving profile photo from phone gallery | Change profile image with gallery option | Minor | low | FC | ----------- | ------------------- | Gaurank | ------------------- |  | OPEN
91 | BG27 | 2022-06-28 |  | Name changed without any error | First name change with special character | Minor | low | UI | ----------- | ------------------- | Gaurank | ------------------- |  | OPEN
93 | BG28 | 2022-06-28 |  | Name changed without any error | First name change with numbers | Minor | low | UI | ----------- | ------------------- | Gaurank | ------------------- |  | OPEN
97 | BG29 | 2022-06-28 |  | Name changed without any error | Second name change with special character | Minor | low | UI | ----------- | ------------------- | Gaurank | ------------------- |  | OPEN
98 | BG30 | 2022-06-28 |  | Name changed without any error | Second name change with numbers | Minor | low | UI | ----------- | ------------------- | Gaurank | ------------------- |  | OPEN
103 | BG31 | 2022-06-28 |  | It change till 23 hours | Change time availability | Minor | low | UI | ----------- | ------------------- | Gaurank | ------------------- |  | OPEN
109 | BG32 | 2022-06-28 | How it works | No button available | Back button for main menu from how it works | Minor | low | UI | ----------- | ------------------- | Gaurank | ------------------- |  | OPEN
119 | BG33 | 2022-06-28 | Contact us | Button not working | Contact us back button is working | Minor | low | FC | ----------- | ------------------- | Gaurank | ------------------- |  | OPEN
126 | BG34 | 2022-06-28 |  | While selecting data it redirected to home page | select and cope data | Minor | low | FC | ----------- | ------------------- | Gaurank | ------------------- |  | OPEN
132 | BG35 | 2022-06-28 | Tab buttons | Take time to open tabs and some time skips tab | Click tab button instantly | Minor | low | FC | ----------- | ------------------- | Gaurank | ------------------- |  | OPEN
410 | BG36 | 2022-06-28 | add services | App lags or java error | Add amount more than lakhs | Minor | low | FC | ----------- | ------------------- | Gaurank | ------------------- |  | OPEN
411 | BG37 | 2022-06-28 |  | No character limit available for amount | Character limit for amount | Minor | low | UI | ----------- | ------------------- | Gaurank | ------------------- |  | OPEN
448 | BG38 | 2022-06-28 | Manage portfolio | Failed to upload photo from Google gallery in android 11 | Try to add image from Google gallery | Minor | low | FC | ----------- | ------------------- | Gaurank | ------------------- |  | OPEN
458 | BG39 | 2022-06-28 |  | Failed to upload photo from Google gallery in android version 11 | Try to add image from Google gallery | Minor | low | FC | ----------- | ------------------- | Gaurank | ------------------- |  | OPEN